## Sheet1
Risk | Risk Resolution Measures | Justification
Personnel Shortfalls | Staffing with top talent & key peronnel agreements | By staffing top talent, there is less likehood of absence during the course of the project.
Developing the wrong user interface | Prototyping, Scenarios, Task analysis, User participation | With the use of prototyping, scenarios, & task analysis, user involvement is increased; which ensures that the correct user interface is developed.
Shortfalls in externally funished components | Benchmarking, inspections, compability analysis | Benchmarking & inspections ensure that the externally furnished meet certain criteria or standards. Combined with a compability analysis, shortfalls can be reduced more effectively.
Shortfalls in externally performed tasks | Reference checking, Competitve design or prototyping, Team-building | Team building ensures that externally performed tasks are executed accordingly.
Real-time performance shortfalls | Simulation, Modeling, Tuning | Through the use of simulation, modeling, & tuning, real time performance can be maximized.